## Sche
| Date |  | Date |  | Date |  | Date |  | Date |  | ROLE/ACTIVITY | PARTICIPANTS | DAY | HOUR | PROJECT
| 2026-10-05 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-08 |  | 2026-10-09
8:55 | Connection Test | 8:55 | Connection Test | 8:55 | Connection Test | 8:55 | Connection Test | 8:55 | Connection Test |  | Briefing & Final Findings | All participants + sponsor |  | See schedule | ALL
9:00 | Appraisal participants briefing | 9:00 | Team Planning | 9:00 | Team Planning | 9:00 | Team Planning | 9:00 | Team Planning |  | Mini-Teams debrief | ATMs |  | See schedule | ATM |  | P1 | P2 | P3
9:15 |  | 9:15 |  | 9:15 |  | 9:15 |  | 9:15 |  |  | EPG | Ana L. Fragoso C. | 2026-10-05 | See schedule | ALL | 1
9:30 | Review Evidence and Team Training | 9:30 | Human Resources (OT) | 9:30 | Configuration Manager (CM) | 9:30 | Findings Consolidation | 9:30 | Preliminary Findings & Performance Report Review |  |  | Karen Ailine Espinoza |  |  |  | 1
9:45 |  | 9:45 |  | 9:45 |  | 9:45 |  | 9:45
10:00 |  | 10:00 |  | 10:00 |  | 10:00 |  | 10:00 |  |  | QA(Quality Assurance) | Luis Erick Rodríguez | 2026-10-05 | See schedule | ALL | 1
10:15 |  | 10:15 |  | 10:15 |  | 10:15 |  | 10:15
10:30 | SM GOV, II | 10:30 | Review Evidence and Team Training | 10:30 | Review Evidence and Team Training | 10:30 |  | 10:30 |  |  | OT | Florencia Vitale | 2026-10-06 | See schedule | ALL | 1
10:45 |  | 10:45 |  | 10:45 |  | 10:45 |  | 10:45 | Preliminary Findings
11:00 |  | 11:00 |  | 11:00 |  | 11:00 |  | 11:00 |  |  | CM | Carlos Quintero N. | 2026-10-07 | See schedule | ALL | 1
11:15 |  | 11:15 |  | 11:15 |  | 11:15 |  | 11:15 | Follow-up 2 |  | Sr. Management | Oscar Vera | 2026-10-05 | See schedule | ALL | 1
11:30 | Break | 11:30 | PM2 (EST, PLAN, MC,) | 11:30 | FAR 02 (VV, PR,) | 11:30 | Review Findings Consolidation | 11:30
11:45 | EPG PAD, PCM, MPM | 11:45 |  | 11:45 |  | 11:45 |  | 11:45 | Finalize Findings and Ratings
12:00 |  | 12:00 |  | 12:00 |  | 12:00 |  | 12:00 |  |  | Requirements | Carlos Quintero N. | 2026-10-07 | See schedule | P1 |  | 0
12:15 |  | 12:15 |  | 12:15 |  | 12:15 |  | 12:15 |  |  |  | 0 |  |  | P2
12:30 |  | 12:30 |  | 12:30 |  | 12:30 |  | 12:30 |  |  |  | 0 |  |  | P3
12:45 | Break | 12:45 |  | 12:45 | Break | 12:45 | Follow-up 1 | 12:45 |  |  | PM | Carlos Quintero N. | 2026-10-06 | See schedule | P1 |  | 0
13:00 | QA (PQA) | 13:00 | Break | 13:00 | FAR 01 (DAR, TS, PI) | 13:00 | Characterize and Create Preliminary Findings | 13:00 | Final Findings & Performance Report presentation. |  |  | Miguel A. López H. |  |  | P2 |  |  | 1
13:15 |  | 13:15 | PM1 (RDM, RSK, CAR) | 13:15 |  | 13:15 |  | 13:15 |  |  |  | 0 |  |  | P3
13:30 |  | 13:30 |  | 13:30 |  | 13:30 |  | 13:30 |  | des | FAR01 ENGINEERING | 0 | 2026-10-07 | See schedule | P1
13:45 |  | 13:45 |  | 13:45 |  | 13:45 |  | 13:45 |  | des |  | Miguel A. López H. |  |  | P2 |  |  | 0
14:00 | Lunch | 14:00 |  | 14:00 |  | 14:00 |  | 14:00 | Lunch | des |  | 0 |  |  | P3
14:15 |  | 14:15 |  | 14:15 |  | 14:15 |  | 14:15 |  | dev |  | 0 |  |  | P1
14:30 |  | 14:30 |  | 14:30 | Lunch | 14:30 |  | 14:30 |  | dev |  | 0 |  |  | P1
14:45 |  | 14:45 | Lunch | 14:45 |  | 14:45 |  | 14:45 |  | dev |  | 0 |  |  | P1
15:00 |  | 15:00 |  | 15:00 |  | 15:00 | Lunch | 15:00 |  | dev |  | 0 |  |  | P2
15:15 |  | 15:15 |  | 15:15 |  | 15:15 |  | 15:15 | Contingency block | dev |  | Miguel A. López H. |  |  | P2 |  |  | 0
15:30 | Evidence Review & Preliminary Findings | 15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | dev |  | 0 |  |  | P2
15:45 |  | 15:45 |  | 15:45 |  | 15:45 |  | 15:45 |  |  |  | 0 |  |  | P3 |  | 0
16:00 |  | 16:00 |  | 16:00 | Evidence Review & Preliminary Findings | 16:00 |  | 16:00 |  |  |  | 0 |  |  | P3 |  | 0
16:15 |  | 16:15 | Evidence Review & Preliminary Findings | 16:15 |  | 16:15 |  | 16:15 |  |  |  | 0 |  |  | P3
16:30 |  | 16:30 |  | 16:30 |  | 16:30 | Contingency block | 16:30 |  | test | FAR02 TESTING | Rodolfo Hernandez | 2026-10-07 | See schedule | P1 |  | 1
16:45 |  | 16:45 |  | 16:45 |  | 16:45 |  | 16:45 |  | test |  | 0 |  |  | P3
17:00 |  | 17:00 |  | 17:00 |  | 17:00 |  | 17:00 |  | test |  | 0 |  |  | P3
[16 empty] | 6 | 1 | 1 | 0
[12 empty] | Participants and projects marked in blue in this schedule will be the minimum sample review for appraisal per SAMPLING APPROVAL |  |  |  |  | P1 | P2 | P3
8
| Important Notes: | [9 empty] | *Sponsor must attend the opening briefing and the final presentation
The Appraisal must be executed according to this plan and schedule approved by the sponsor.
Appraisal team will work according to the schedule. All Virtual activities are scheduled to consider a timeframe that goes from 10:00 AM to 6:00 PM, considering 1-2 hours for lunch and breaks for refresh. If necessary the ATM must work late if any contingencies arise.
If determined there are feasibility concerns, ATL must discuss with the appraisal sponsor and keep the appraisal plan and schedule updated.
Formulas:
Date = [Date]+1

## MTs
preguntas
MT1 |  |  |  | GOV 2.1, 2.4, 3.1, 3.2
Participants | PAs assigned |  |  | II 2.2, 3.1, 3.2, 3.3,
Luis Erick Rodríguez | GOV, II, MPM, PCM, PAD, PQA |  |  | MPM 2.1, 3.3, 2.3, 2.4, 3.5
Florencia Vitale | OT, EST, PLAN, MC, RSK, CAR, DAR |  |  | PCM 3.1, 3.2, 2.1,3.5, 3.6
MT2 |  |  |  | PAD 3.2, 2.2, 3.3, 2.3, 3.4, 3.6
Participants | PAs assigned |  |  | PQA 2.1, 2.2, 3.1, 2.3, 2.4
Rodolfo Alfonso Hernández | CM, RDM, TS, PI, PR, VV
Jesús Sánchez
Team Member Name | Organizational Affiliation | Years of Development Domain Experience | Years of Management Experience
Luis Erick Rodríguez | Four J's Development Tools Latinoamérica.
Florencia Vitale | Four J's Development Tools Latinoamérica.
Rodolfo Alfonso Hernández | Four J's Development Tools Latinoamérica.
Carlos Quintero N. | Four J's Development Tools Latinoamérica.
Team Member Name | Organizational Affiliation |  | Name | CMMI DEV | Field Experience | Management Experience | High Maturity Experience | Appraisal Responsibilities
Jesus Sanchez | Independent consultant |  | Jesús Sánchez | V2.0 | 32 | 31 | 11 | SLA
Luis Erick Rodríguez | Four J's Development Tools Latinoamérica. |  | Type of Domain Experience | High Maturity Concepts |  |  | Specific Responsibilities | PAD, PCM, CAR, MPM, MC, RDM, VV, GOV, II
Florencia Vitale | Four J's Development Tools Latinoamérica. |  |  | Project Management.
Rodolfo Alfonso Hernández | Four J's Development Tools Latinoamérica. |  |  | Test Engineering.
Design Engineering
OU Coordinator | Four J's Development Tools Latinoamérica. |  |  | Requirements specification
Carlos Quintero N. |  |  |  | Root Cause analysis specialist
Project planning and management
Sponsor | Oscar Vera |  |  | Management experience (including team lead)
Measurement & Analysis
Process quality assurance and improvement
Quantitative management (e.g., Six Sigma)
Note on G20: Jesús Sánchez: marzo 1992 a marzo 2024
Note on H20: Jesús Sánchez: ene 1993 a ene 2024
Note on I20: Jesús Sánchez: ene 2011 a ene 2021

## projects
Subgroup | Project | EDP Engineering and Developing Products |  | ENQ Ensuring Quality |  |  |  | IMP Improving Performance |  |  | MBR Managing Business Resilience | MWF Managing the Workforce | PMW Planning and Managing Work |  |  | SI Supporting Implementation
|  | PI Product Integration | TS Technical Solution | PQA Process Quality Assurance | PR Peer Reviews | RDM Requirements Development and Management | VV Verification and Validation | MPM Managing Performance and Measurement | PAD Process Asset Development | PCM Process Management | RSK Risk and Opportunity Management | OT Organizational Training | EST Estimating | MC Monitor and Control | PLAN Planning | CAR Causal Analysis and Resolution | CM Configuration Management | DAR Decision Analysis and Resolution
SG1 | P1- Portability ISSSTE (Required Project) | SE | SE | RS | RS | RS | RS | SE | SI | SI | RS | SI | SE | SE | SE | RS | ADD | RS
SG2 | P2- Improvements to TG7 | RS | RS | SE | SE | SE | SE | ADD | SI | SI | SE | SI | RS | RS | RS | SE | SE | SE
CM Staff | bar: SE RS to RS SE
EPG Staff | bar: SE RS to RS SE
OT Staff | bar: SE RS to RS SE
| QA Staff | SI | SI | ADD | SI | SI | SI | SI | SI | SI | SI | SI | SI | SI | SI | SI | SI | SI

## participants
ROLE/ACTIVITY | PARTICIPANTS |  | Participant's Full Name (required) | Participant's Role (required) | Function (required) | PA | Participant's Full Name (required) | Participant's Role (required) | Function (required) | PA
EGP | Ana L. Fragoso C. |  | Oscar Vera | SM | OU | GOV, II | Oscar Vera | SM | OU | GOV, II
|  |  | Ana L. Fragoso C. | EPG | OU | MPM, | Ana L. Fragoso C. | EPG | OU | PCM, PAD, MPM
|  |  | Florencia Vitale | OT | OU | OT | Karen Ailine Espinoza | EPG | OU | PCM, PAD,
QA (Quality Assurance) | Luis Erick Rodríguez |  | Luis Erick Rodríguez | QA | OU | PQA |  | EPG | OU | PCM, PAD, MPM
|  |  | Carlos Quintero N. | CM | OU | CM | Florencia Vitale | OT | OU | OT
OT | Florencia Vitale |  | Carlos Quintero N. | PM | P1 | RSK, CAR, DAR |  | QA | OU | PQA
|  |  | Miguel A. López H. | PM | P2 | EST, PLAN, MC | Luis Erick Rodríguez | QA | OU | PQA
CM | Carlos Quintero N. |  |  | PM | P3 | EST, PLAN, MC, RSK, CAR | Carlos Quintero N. | CM | OU | CM
Sr. Management | Oscar Vera |  | Carlos Quintero N. | Requirement | P1 | RDM |  | CM | OU | CM
|  |  |  | Requirement | P2 | RDM | Carlos Quintero N. | PM | P1 | EST, PLAN, MC, RSK, CAR
|  |  |  | Requirement | P3 | RDM | Miguel A. López H. | PM | P2 | EST, PLAN, MC, RSK, CAR
RDM (Requirements) | Carlos Quintero N. |  |  | Designer | P1 | TS, DAR |  | PM | P3 | EST, PLAN, MC, RSK, CAR
| 0 |  | Miguel A. López H. | Designer | P2 | TS | Carlos Quintero N. | Requirement | P1 | RDM
| 0 |  |  | Designer | P3 | TS |  | Requirement , | P2 | RDM
PMO | Carlos Quintero N. | [6 empty] | Designer | P1 | TS, DAR
| Miguel A. López H. |  |  | Engineer | P1 | PI | Miguel A. López H. | Designer | P2 | TS, DAR
| 0 |  |  | Engineer | P1 | PI |  | Designer | P3 | TS, DAR
FAR 01 | 0 | P1 |  | Engineer | P1 | PI | Miguel A. López H. | Developer | P2 | PI, PR
| Miguel A. López H. | P2 | Miguel A. López H. | Engineer | P2 | PI, |  |  | P1 | PI
| 0 | P3 |  | Engineer | P2 | PI, PR |  | Engineer | P1, P2, P3 | PI
| 0 | P1 |  | Researcher | P1 | RDM, VV |  |  | P2 | PI
| 0 | P1 |  | Researcher | P1 | RDM, VV |  | Designer | P3 | PI, TS
| 0 | P1 |  | Engineer | P3 | PI |  |  | P3 | PI
| 0 | P2 | Rodolfo Hernandez | Tester | P1 | VV, PR |  |  | P3 | PI
| Miguel A. López H. | P2 |  | Tester | P2 | VV, PR | Rodolfo Hernandez | Tester | P1 | VV, PR
| 0 | P2 |  | Tester | P3 | VV, PR |  | Tester | P2 | VV, PR
| 0 | P3 | [5 empty] | Tester | P3 | VV, PR
| 0 | P3
| 0 | P3
FAR 02 | Rodolfo Hernandez | P1
| 0 | P2
| 0 | P3

## checklist
| Checklist conduct appraisal | Done | Strengths - A type of preliminary or final finding, which is an exemplary or noteworthy implementation of a process that meets the intent and value of a CMMI model practice.
1 | Sign Sponsor, ATMs and Interpreter CONFIDENTIALITY AND NON-ATTRIBUTION in CAS
2 | Schedule
3 | Test conection |  | Weaknesses - A type of preliminary or final finding, which is an ineffective, or lack of, implementation of one or more processes meet the intent and value of a practice based on verified OE, and applicable across the project(s) and organizational support functions or OU as a whole.
4 | Script
5 | Performance report
6 | Findings template |  | Improvement Opportunity - A type of preliminary or Final Findings about a particular process that meets the intent and value of a model practice but represents an opportunity where the process could be improved to provide more value.
7 | ATM pictures in CAS and sponosor verify identity.
8 | Set of documents in each ATM
9 | Train ATM: concepts
10 | Train ATM: caracterization and ratings
11 | Check the license |  | Ensure that all Appraisal Team Members (ATMs) have access to a licensed current version of the CMMI model.